## Sheet1
Steps | Tasks | Description | Estimation(in Hours) | Status | Possible Blockers/Reestimating points
1 | Knowledge Base Creation | Data Collection and storing to Vector DB, Data Source : Web Scraping from Growexx wesbite , relevant document sources | 20 hrs
2 | Connecting Knowledge base to LLM | connecting vector DB to LLM through RAG | 20 hrs
3 | Speech to Text conversion | Creating a model that takes audio as input and convert it to text | 16 hrs
4 | Response Generation | Trying out different LLM models , integrating the llm with Knowledge base and STT model , prompt optimization, enhancing the generated response | 16 hrs
5 | Dataset creation for voice impersonation | Extracting the target voice from a pool of videos , cleaning and enhancing the extracted audio, splitting the audio into nano chunks and storing. | 16 hrs
6 | Voice cloning using open-source tools | Experimenting with different open source tools like metavoice , whisper speech, myshell ai. We only need to provide sample voice and the text input which we want to convert to speech. | 20 hrs |  |  | Documentation not available
7 | Integrating TTS voice cloning tool with LLM | Connecting different components and testing the end to end system | 12 hrs
8 | Voice cloning using open-source models | If the created system does not generate the desired response , then as a improvement we can try voice cloning using open source models like Tortorise Tts , RVC and its variants etc. For this we have to fine tune the model on created dataset | 32 hrs
9 | Integrating TTS voice cloning fine tuned model with LLM | Integrating different models with the system and selecting the model which gives best results/responses | 16 hrs
10 | UI Designing | Designing UI for demostrating the end to end system in form of a chatbot | 24 hrs
11 | Demo Preparation and documentation
12 | Demo/ Presentation
13
| WEEK-01 29/07/23 – 02/08/23 | WEEK-02 05/08/23 -09/08/23 | WEEK-03 12/08/24 – 14/08/24
| Task 1-4 | Task 5-10 | Buffer week for documentation , blockers
| 72 hrs of work will be required | 120 hrs of work required | Demo presentation